## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
File Handling
STORY # 02:
File Handling
STORY # 02 - TASK # 02: Create file handling functions for Signup
STORY # 03 - TASK # 01: Add entries
STORY # 01 - TASK # 01: Create Admin Panel UIs
STORY # 03:
Database
STORY # 05:
Administrator Capabilities
STORY # 04 - TASK # 01: Create functions for administrator features
STORY # 01 - TASK # 02: Improve Login UI
STORY # 01 - TASK # 03: Improve Signup UI
STORY # 04 - TASK # 01: Test Administrator Panel
STORY # 04 - TASK # 01: Improve Administrator Panel

## Availability Estimate
Availability Estimate
weekday | W | TH | F | S | S | M | T
month | October
Resource | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09
Resource | Sprint #3 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Lester | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
Vince | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 56
Until the end of the Sprint | 48 | 40 | 32 | 24 | 16 | 8 | 0
Total per Sprint | 56

## Actual Spent Time
Actual Availability
weekday | W | TH | F | S | S | M | T
month | October
day | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Lester | 4 | 0 | 4 | 2 | 4 | 5 | 6 | 25
Vince | 4 | 0 | 4 | 2 | 4 | 5 | 6 | 25
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 0 | 8 | 4 | 8 | 10 | 12 | 50
Until the end of the Sprint | 48 | 48 | 40 | 36 | 28 | 18 | 6
Total per Sprint | 56

## 3rd Sprint
|  |  |  | 24 | W | TH | F | S | S | M | T
Story | Task | Category | Who | 7 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09
Ideal Execution |  |  |  | 46 | 39.4286 | 32.8571 | 26.2857 | 19.7143 | 13.1429 | 6.5714 | 8.8818e-15
Total per Day |  |  |  | 46 | 34 | 34 | 23 | 14 | 9 | 6 | 0
Ui Design | Design Administrator Panel UIs | Design | Vince | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| Improve Login UI | Improvement | Vince | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Improve Signup Ui | Improvement | Lester | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
0
0
|  |  |  | 0 | [9 empty] | W | TH | F | S | S | M | T
File Handling | Test Signup file handling functions | Handling | Lester | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [7 empty] | Ideal | 46 | 39.4286 | 32.8571 | 26.2857 | 19.7143 | 13.1429 | 6.5714 | 8.8818e-15
|  |  |  | 0 | [7 empty] | Real | 46 | 34 | 34 | 23 | 14 | 9 | 6 | 0
Database | Add Entries | Database | Both | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 0 | Design | 20 | 13 | 13 | 5 | 5 | 0 | 0 | 0
|  |  |  | 0 | [7 empty] | Database | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 0
|  |  |  | 0 | [7 empty] | Handling | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [7 empty] | Testing | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0
Administrator Capability | Create functions for administration features | Design | Lester | 10 | 8 | 8 | 5 | 5 | 0 | 0 | 0 | Improvement | 9 | 9 | 9 | 6 | 0 | 0 | 0 | 0
| Test Administrator Panel | Testing | Vince | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Improve Administrator Panel | Improvement | Both | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | UI Design | Design Administrator Panel Uis
Done! | UI Design | Improve Login UI
Done! | UI Design | Improve Signup UI
Dropped | File Handling | Test Signup file handling functions
Done! | Database | Add Entries
Done! | Administrator Capabilities | Create functions for administration features
Done! | Administrator Capabilities | Test Administrator Panel
Done! | Administrator Capabilities | Improve Administrator Panel
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Design | Lester
0.5 | Done! | Database | Vince
1 | Blocked | Handling | BOTH
2 | Ongoing | Testing
3 | Planned | Improvement
5
8
13
21
34
55
89
∞