## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
File Handling
STORY # 02:
UI Design
STORY # 02 - TASK # 02: Design Signup UI of all users
STORY # 02 - TASK # 01: Design Login UI of all users
STORY # 03 - TASK # 01: Create file handling for Login
STORY # 01 - TASK # 01: Create Login ui for Peer advisers
STORY # 03:
File Handling
STORY # 04:
Database
STORY # 04 - TASK # 01: Create database for records

## Availability Estimate
Availability Estimate
weekday | W | TH | F | S | S | M | T
month | September
Resource | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Lester | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
Vince | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 56
Until the end of the Sprint | 48 | 40 | 32 | 24 | 16 | 8 | 0
Total per Sprint | 56

## Actual Spent Time
Actual Availability
weekday | W | TH | F | S | S | M | T
month | September
day | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Lester | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
Vince | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 56
Until the end of the Sprint | 48 | 40 | 32 | 24 | 16 | 8 | 0
Total per Sprint | 56

## 1st Sprint
|  |  |  | 24 | W | TH | F | S | S | M | T
Story | Task | Category | Who | 7 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25
Ideal Execution |  |  |  | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
Total per Day |  |  |  | 40 | 29 | 27 | 18 | 16 | 13 | 6 | 0
UI Design | Design Login UI of different users | Design | Lester | 10 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Design Signup UI of different users | Design | Lester | 10 | 7 | 7 | 4 | 2 | 0 | 0 | 0
0
0
0
|  |  |  | 0 | [9 empty] | W | TH | F | S | S | M | T
File Handling | Create file handling functions for Login | Handling | Vince | 15 | 13 | 13 | 9 | 9 | 8 | 4 | 0 |  | Estimate | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25
0
|  |  |  | 0 | [7 empty] | Ideal | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
|  |  |  | 0 | [7 empty] | Real | 40 | 29 | 27 | 18 | 16 | 13 | 6 | 0
Database | Create database for records | Database | Lester | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | Design | 20 | 11 | 9 | 4 | 2 | 0 | 0 | 0
|  |  |  | 0 | [7 empty] | Database | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
|  |  |  | 0 | [7 empty] | Handling | 15 | 13 | 13 | 9 | 9 | 8 | 4 | 0
|  |  |  | 0 | [7 empty] | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Administrator Capability |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | UI Design | Design Login UI of different users
Done! | UI Design | Design Signup UI of different users
Done! | File Handling | Create file handling for Login
Done! | Database | Create database for records
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Design | Lester
0.5 | Done! | Database | Vince
1 | Blocked | Handling | Both
2 | Ongoing | Testing
3 | Planned | Improvement
5
8
13
21
34
55
89
∞