## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
File Handling
STORY # 02:
Database
STORY # 02 - TASK # 02: Create file handling functions for Signup
STORY # 02 - TASK # 01: Test Login file handling functions
STORY # 03 - TASK # 01: Add entries
STORY # 02 - TASK # 01: Add Signup in user manual
STORY # 01 - TASK # 01: Create Login ui for Peer advisers
STORY # 04:
User Manual
STORY # 03:
Database
STORY # 05:
Administrator Capabilities
STORY # 02 - TASK # 01: Create adminsitrator functions

## Availability Estimate
Availability Estimate
weekday | W | TH | F | S | S | M | T
month | September
Resource | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02
Resource | Sprint #2 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Lester | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
Vince | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 28
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 56
Until the end of the Sprint | 48 | 40 | 32 | 24 | 16 | 8 | 0
Total per Sprint | 56

## Actual Spent Time
Actual Availability
weekday | W | TH | F | S | S | M | T
month | September
day | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Lester | 4 | 2 | 1 | 0 | 1 | 1 | 4 | 13
Vince | 4 | 3 | 4 | 0 | 1 | 4 | 4 | 20
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 5 | 5 | 0 | 2 | 5 | 8 | 33
Until the end of the Sprint | 48 | 43 | 38 | 38 | 36 | 31 | 23
Total per Sprint | 56

## 2nd Sprint
|  |  |  | 24 | W | TH | F | S | S | M | T
Story | Task | Category | Who | 7 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02
Ideal Execution |  |  |  | 43 | 36.8571 | 30.7143 | 24.5714 | 18.4286 | 12.2857 | 6.1429 | 0
Total per Day |  |  |  | 43 | 38 | 29 | 25 | 24 | 23 | 19 | 15
Ui Design |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
|  |  |  | 0 | [9 empty] | W | TH | F | S | S | M | T
File Handling | Test Login file handling functions | Handling | Vince | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02
| Create file handling functions for Signup | Handling | Vince | 15 | 13 | 13 | 9 | 9 | 8 | 4 | 0
|  |  |  | 0 | [7 empty] | Ideal | 43 | 36.8571 | 30.7143 | 24.5714 | 18.4286 | 12.2857 | 6.1429 | 0
|  |  |  | 0 | [7 empty] | Real | 43 | 38 | 29 | 25 | 24 | 23 | 19 | 15
Database | Add Entries | Database | Lester | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Design | 15 | 14 | 13 | 13 | 12 | 12 | 12 | 12
|  |  |  | 0 | [7 empty] | Database | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  |  | 0 | [7 empty] | Handling | 20 | 16 | 13 | 9 | 9 | 8 | 4 | 0
|  |  |  | 0 | [7 empty] | Documentation | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
User Manual | Add Signup in user manual | Documentation | Vince | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Administrator Capability | Create functions for administrator feature | Design | Lester | 15 | 14 | 13 | 13 | 12 | 12 | 12 | 12
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | File Handling | Test Login file handling functions
Done! | File Handling | Create file handling functions for Signup
Ongoing | Database | Add entries
Done! | User Manual | Add Signup in user manual
Planned | Administrator Capabilities | Create functions for administrator features
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Design | Lester
0.5 | Done! | Database | Vince
1 | Blocked | Handling | BOTH
2 | Ongoing | Documentation
3 | Planned | Testing
5 |  | Improvement
8
13
21
34
55
89
∞